## Content Calendar
EcocomityChain.AI · PMG Platform — Content Calendar
12-Week Programme · Sequenced narrative arc: Problem → Architecture → Proof → Urgency → Invitation
Week | Phase | Channel | Title / Topic | Status | Owner | Target Date | Word Count / Format | Dependencies | Notes | Seq #
1 | Phase 1 · Problem | Blog | The Q4 Problem: What Ford and MIT Discovered, and What Material Depth Reveals Next | Ready | Founder | Week 1 | ~1,050 words | Article text + Visual 1 (EPS TTR diagram) — both complete | Ford-MIT TTR-PI blog. Publish first. Sets the intellectual tone. Files: Blog_TTR_FordMIT_Article.md + EPS_TTR_DualPath_Visual1.html (EPS dual-path TTR diagram, dark theme, screenshot to PNG for Wix). | 1
1 | Phase 1 · Problem | LinkedIn – Company | Short-form: The Q4 hidden risk cluster — what Ford's MIT study actually proved | Planned | Founder | Week 1 | ~250 words + graphic | Blog (item 1) published first | Distilled version of Ford-MIT finding. Link to blog. | 2
2 | Phase 1 · Problem | LinkedIn – Founder | The question I keep asking CPOs — and the answer nobody has | Planned | Founder | Week 2 | ~400 words | None | Personal framing of the sub-tier visibility gap. No product mention. Problem-only post. | 3
2 | Phase 1 · Problem | LinkedIn – Company | Did You Know series #1 — Supplier maps end at Tier 2 | Planned | Founder | Week 2 | ~200 words + stat graphic | None | 'Did you know that most supply chain risk tools stop at Tier 2? Here is what lives below.' Infographic or screenshot. | 4
3 | Phase 1 · Problem | Blog | Five Supply Chain Disruptions That Supplier-Level Tools Could Not Predict | Planned | Founder | Week 3 | ~1,200 words | Renesas + GOES confirmed; 3 modelled scenarios. Framing agreed. | Two documented (Renesas 2021, GOES post-Ukraine) + three illustrative. Clear framing for each category. | 5
3 | Phase 1 · Problem | LinkedIn – Company | Short-form: The Renesas fire and the semiconductor dependency nobody mapped | Planned | Founder | Week 3 | ~250 words | Item 5 published | Link to five disruptions blog. | 6
4 | Phase 1 · Problem | LinkedIn – Founder | Why we built a material graph instead of a supplier graph — the decision that changed everything | Planned | Founder | Week 4 | ~500 words | None | Founder origin story. Authentic, no fabrication. Explains why material ≠ supplier. | 7
5 | Phase 2 · Architecture | Blog | What No Competitor Can Map — The Material Genealogy Argument | Planned | Founder | Week 5 | ~1,000 words | IP boundary agreed: conceptual, no schema/weights | Differentiates PMG architecture without exposing implementation. Written to stand alone. | 8
5 | Phase 2 · Architecture | LinkedIn – Company | Did You Know series #2 — Eight levels deep: what exists below your T2 suppliers | Planned | Founder | Week 5 | ~200 words + diagram | Item 8 published | Companion post to material genealogy blog. | 9
6 | Phase 2 · Architecture | Blog | Dual-Node Risk Scoring — Why Scoring Suppliers and Materials Simultaneously Requires a Different Architecture | Planned | Founder | Week 6 | ~900 words | IP boundary: outputs and concept only. No scoring weights. | Conceptual differentiation post. Aimed at technical evaluators and integrator partners. | 10
6 | Phase 2 · Architecture | LinkedIn – Founder | Why we chose Neo4j over a relational database for this problem | Planned | Founder | Week 6 | ~400 words | None | Technical founder post. Attracts integrator and engineering audience. | 11
7 | Phase 2 · Architecture | Blog | Graph-Native Supply Chain Risk — A Neo4j Perspective [Co-marketing] | Planned | Founder + Neo4j | Week 7 | ~1,000 words | Neo4j partnership progression required | Draft ready once Neo4j partnership is formalised. Can write in advance. | 12
7 | Phase 2 · Architecture | LinkedIn – Company | PMG + Neo4j: what graph-native supply chain risk looks like at L8 | Planned | Founder | Week 7 | ~250 words | Item 12 published | Co-marketing post. Tag Neo4j. | 13
8 | Phase 3 · Proof & Urgency | Blog | How Material Genealogy Accelerates DPP — and What That Means for EU Battery Regulation and Other Regulatory Concerns | On Hold | Founder | Week 8 | ~1,000 words | Copilot agent detail on DPP data loading methodology required. Key source: NREL USLCI (full openLCA-structured dataset from NREL). Also DOE Critical Minerals. Scope by product type + supplier region. | REFRAMED. Argument: ECC gives OEMs ~80% DPP baseline before first supplier questionnaire. What that means for EU Battery Regulation, CBAM, and other regulatory deadlines. Do NOT expose manufacturing process initialisation logic. | 14
8 | Phase 3 · Proof & Urgency | LinkedIn – Company | Regulatory countdown: EU Battery Regulation enforcement is approaching — here is where most OEMs stand | Planned | Founder | Week 8 | ~200 words | None | Deadline-driven urgency post. No product pitch. | 15
9 | Phase 3 · Proof & Urgency | Blog | Early Warning Signals: What OSINT-Based Intelligence Sees Before Quarterly Financials Do | Planned | Founder | Week 9 | ~1,000 words | SV PDF required (user to provide in next conversation). SV partnership not yet signed — do NOT name SV in content. | REFRAMED (was TTR-PI case study — that angle is complete in the Ford-MIT blog). Argument: OSINT signals flag supplier financial distress weeks/months before quarterly financials (e.g. RapidRatings) reflect it. ECC ingests 'partner-provided signals' alongside material genealogy graph. Three-part narrative: signals → structure → action path. | 16
9 | Phase 3 · Proof & Urgency | LinkedIn – Founder | By the time your financial risk provider flags a distressed supplier, the window for action may already be closed. Here is what advance signals look like. | Planned | Founder | Week 9 | ~500 words | Item 16 published | Reframed to match the early warning angle of the blog (item 16). Follows item 20 publication. | 17
10 | Phase 3 · Proof & Urgency | LinkedIn – Company | Did You Know series #3 — What tariff exposure looks like when your BOM is already scored | Planned | Founder | Week 10 | ~200 words + screenshot | Tariff layer live | Platform capability post. Before/after framing for tariff scoring. | 18
10 | Phase 3 · Proof & Urgency | Video | What hides below Tier 2 in your supply chain — 2-min explainer | Planned | Founder | Week 10 | 90–120 sec script + visuals | Blog content complete | Script: iceberg visual, one stat, one killer question. Founder on camera or voiceover. | 19
11 | Phase 3 · Proof & Urgency | Video | The substitution trap: why component-level decisions need L8 data | Planned | Founder | Week 11 | 90–120 sec | Slide 3 stories content | SmCo/NdFeB story told as a 2-min video. Strong hook for automotive engineers. | 20
12 | Phase 4 · Invitation | Document | Conversation Starter — for LinkedIn consultants and supply chain advisors | Planned | Founder | Week 12 | 2 pages PDF | Blog content complete | Leave-behind document. Problem framing + one sharp talking point. Written for forwards. | 21
12 | Phase 4 · Invitation | Document | Pilot Offer — What we show you in 30 days from one plant and one vehicle line | Planned | Founder | Week 12 | 1 page PDF | None | Removes the barrier to a first conversation. Scoped value demonstration, not pricing. | 22
12 | Phase 4 · Invitation | LinkedIn – Company | What we can show you in 30 days — one plant, one vehicle line | Planned | Founder | Week 12 | ~200 words | Item 22 complete | Soft launch of pilot offer. CTA to contact. | 23
— | Ongoing | LinkedIn – Company | Did You Know series (ongoing) — one new material / supply chain fact per week | Planned | Founder | Weekly | ~150–200 words each | Batch-draft 8–10 in advance | Series continues throughout programme. | 24
— | Ongoing | LinkedIn – Company | Product milestone posts — graph scale, layer launches, partnership announcements | Planned | Founder | As needed | ~150 words each | Milestone occurs | Factual, specific. No hype. | 25
— | Ongoing | LinkedIn – Founder | Analytical posts on live supply chain events (tariff announcements, disruptions) | Planned | Founder | As needed | ~400 words | Event occurs | React to live news with analytical depth. Builds credibility as a real-time thinker. | 26
— | Backlog – Partnership | Partnership | Combined post: ECC + Semantic Visions — how OSINT signals and material genealogy work together | On Hold | Founder | Post-partnership | ~800 words blog + LinkedIn | SV partnership signed + PDF shared | Draft the argument now. Publish only after commercial terms signed. | 27
— | Backlog – Partnership | Partnership | Combined post: ECC + Total Materia — material substitution intelligence + supply chain risk | On Hold | Founder | Post-partnership | ~800 words blog + LinkedIn | Total Materia partnership formalised | Same structure as SV post. | 28
— | Backlog – Partnership | Partnership | Neo4j Customer Advocacy — brief for Neo4j team on how to talk about PMG to their customers | On Hold | Founder | Post-partnership | 1-page brief | Neo4j advocacy team engagement confirmed | A one-pager written for a Neo4j customer, not a PMG prospect. | 29
— | Engineering Excellence · Series | Blog | Cross-Cutting Context Objects: Threading Structured Evidence Through a Multi-Engine Pipeline | Ready | Founder | Week 2–3 (publish early in the mix) | ~2,200 words · 2 diagrams | COMPLETE. Blog text + 2 diagrams built and ready. | Engineering Excellence Blog 2 — publishes FIRST in the series. Uber/Netflix engineering style. Files: Blog2_CrossCuttingContext_REVISED.md + Diagram1_ExplanationContext_Flow.html + Diagram2_ExplanationStep_Anatomy.html (open in Chrome → DevTools → Capture full size screenshot → upload PNG to Wix). Diagram 3 (Dual Consumer Fork) dropped as redundant. IP note: reference to 'write fence' not 'Guardrail G8'. | 30
— | Parallel Workstream | Document | Data-Driven White Paper — The Material Genealogy Case for Supply Chain Risk | In Progress | Founder | Parallel workstream — begin when user signals readiness | 6–8 pages | Begin when user signals readiness. Does NOT wait for blog programme to complete. | DECISION: parallel workstream, not deferred to Month 4. Structure: problem → data architecture argument → science validation → three documented disruptions → pilot framing. IP-protected throughout. Cite USGS/DOE/Argonne GREET. | 31
— | Deferred | Document | Analyst Briefing Document — for Gartner / Forrester / IDC outreach | Deferred | Founder | Month 5 | 2 pages, no sales language | First customer or pilot signed | 2-page technical positioning for analyst briefings. | 32
— | Deferred | Blog | Conference Abstract — 'What No Supplier Map Can See' (AutoSens / Automotive Logistics) | Deferred | Founder | After first pilot | 500-word abstract | Pilot case study available | Title works as both blog and 20-min conference talk. | 33
— | Engineering Excellence · Series | Blog | Deterministic Cores, Agentic Shells — An Architecture Pattern for AI-Augmented Computation | Planned | Founder | After Blog 2 published | ~2,000 words · 3 diagrams | Blog 2 (XAI post) published first. Engineering content from VS Code Copilot required. | Engineering Excellence Blog 1 (publishes 2nd in series). Three-layer separation: deterministic engines → agentic orchestration → SOP-constrained tools. Includes the FTA placement bug before/after. Crash-safety property explained. Diagrams: Three-Layer Stack, Crash Safety Decision Tree, FTA Bug Before/After. | 34
— | Engineering Excellence · Series | Blog | Phase-Ordered Graph Computation — Batch Pre-Compute Across 170K Interconnected Nodes | Planned | Founder | Engineering series (3rd) | ~2,200 words · 4 diagrams | Engineering content from VS Code Copilot required. | Engineering Excellence Blog 3 (publishes 3rd in series). 11 Cypher-native phases in dependency order inside Neo4j — not application-side. PENDING checkpoint pattern. 170K nodes in ~45s, API reads <100ms. Algorithm degeneracy analysis: betweenness centrality vs custom diamond detection. Diagrams: Phase Dependency DAG, PENDING Checkpoint 3-panel, Algorithm Before/After, Batch vs Read Timeline. | 35
— | Engineering Excellence · Series | Blog | State Machines as Agent Guardrails — Constraining Autonomous Workflows Through Explicit Transitions | Planned | Founder | Engineering series (4th) | ~1,800 words · 3 diagrams | Engineering content from VS Code Copilot required. | Engineering Excellence Blog 4 (publishes 4th in series). 6-state machine (SCORED_CONSERVATIVE → INTELLIGENCE_CONFIRMED → SUPPLIER_DECLARED → ATTESTED_CONFIRMED → SCORED_EXEMPT/CONFIRMED). Tool-level guardrails vs prompt-level. IP NOTE: reference guardrails as 'write fence' — do NOT use internal numbering (G8 etc.). Diagrams: 6-State Machine, Guardrail Enforcement Layers, Rejected State Skip sequence. | 36
— | Engineering Excellence · Series | Blog | Additive Extensibility — Engineering a System That Grows by Configuration, Not Code Modification | Planned | Founder | Engineering series (5th) | ~1,800 words · 4 diagrams | Engineering content from VS Code Copilot required. | Engineering Excellence Blog 5 (publishes 5th in series). Weight auto-normalization, schema-driven engine registration, predicate-based UI rendering, file-per-SOP isolation. Honest assessment: 3 hardcodes that violate additive principle (USD thresholds, US-centric HS code regex, single-country tariff state machine). Diagrams: Weight Auto-Normalization, Phase Manifest Registration, Predicate UI Flow, Three Hardcodes Gap Map. | 37
— | Deferred | Blog | Orchestrating Reactive Resilience — How a Small Model Makes Fast, Scoped Decisions in a Supply Chain Copilot | Deferred | Founder | After founder LinkedIn post on copilot architecture | ~1,200 words | Founder LinkedIn post on copilot system architecture decisions must publish first. Reference: https://developer.nvidia.com/blog/train-small-orchestration-agents-to-solve-big-problems/ | Nvidia NIM 8B orchestrator. Currently in reactive resilience. Used as-is — NOT fine-tuned. Architecture discussion at moderate level OK; copilot subsystem code not open-sourced. Goal: engineering credibility + invite engagement from practitioners. Preceded by founder LinkedIn post covering copilot system design decisions across data, agents, cloud engineering, and system architecture. | 38

## Master Tracker
EcocomityChain.AI · PMG Content Programme — Master Tracker
Use this sheet to track completion. Update Status column as items move through the pipeline.
# | Channel | Title / Topic | Status | Target Week | Published Date | URL / File Location | Word Count | Visual Assets | Notes
1 | Blog | The Q4 Problem: Ford-MIT TTR-PI and Material Depth | Ready | Week 1 |  | Blog_TTR_FordMIT_Article.md | ~1,050 | EPS_TTR_DualPath_Visual1.html → PNG | Article text + visual complete. Open HTML in Chrome → DevTools → Capture full size screenshot → upload PNG to Wix inline.
2 | LinkedIn – Company | Short-form: The Q4 hidden risk cluster | Planned | Week 1 |  |  | ~250 | None | Repurpose from blog intro.
3 | LinkedIn – Founder | The question I keep asking CPOs | Planned | Week 2 |  |  | ~400 | None | Problem-framing post. No product.
4 | LinkedIn – Company | Did You Know #1 — Supplier maps end at T2 | Planned | Week 2 |  |  | ~200 | Stat graphic | Create simple dark stat card.
5 | Blog | Five Supply Chain Disruptions | Planned | Week 3 |  |  | ~1,200 | Optional: simple timeline graphic | Renesas + GOES documented; 3 illustrative. Clear category labels.
6 | LinkedIn – Company | Short-form: Renesas fire | Planned | Week 3 |  |  | ~250 | None | Link to blog item 5.
7 | LinkedIn – Founder | Why we built a material graph | Planned | Week 4 |  |  | ~500 | None | Founder origin story.
8 | Blog | What No Competitor Can Map — Material Genealogy Argument | Planned | Week 5 |  |  | ~1,000 | None | IP guard: conceptual only.
9 | LinkedIn – Company | Did You Know #2 — Eight levels deep | Planned | Week 5 |  |  | ~200 | Diagram/screenshot | Use PMG Tree screenshot.
10 | Blog | Dual-Node Risk Scoring Architecture | Planned | Week 6 |  |  | ~900 | None | Concept-level. No weights.
11 | LinkedIn – Founder | Why we chose Neo4j | Planned | Week 6 |  |  | ~400 | None | Technical founder post.
12 | Blog | Graph-Native Supply Chain Risk [Neo4j co-marketing] | Planned | Week 7 |  |  | ~1,000 | None | Requires Neo4j partnership progress.
13 | LinkedIn – Company | PMG + Neo4j at L8 | Planned | Week 7 |  |  | ~250 | None | Co-marketing post.
14 | Blog | How Material Genealogy Accelerates DPP — and What That Means for EU Battery Regulation and Other Regulatory Concerns | On Hold | Week 8 |  |  | ~1,000 | None | REFRAMED. On hold pending Copilot agent DPP data loading detail. Key source: NREL USLCI (openLCA). Scope by product + supplier region.
15 | LinkedIn – Company | Regulatory countdown post | Planned | Week 8 |  |  | ~200 | None | Deadline urgency.
16 | Blog | Early Warning Signals: What OSINT-Based Intelligence Sees Before Quarterly Financials Do | On Hold | Week 9 |  |  | ~1,100 | None | REFRAMED as early warning system post. On hold: SV PDF required. Do NOT name SV until partnership signed.
17 | LinkedIn – Founder | By the time your financial risk provider flags a distressed supplier, the window for action may already be closed. | On Hold | Week 9 |  |  | ~500 | None | Reframed to match early warning angle. Follows item 19 publication.
18 | LinkedIn – Company | Did You Know #3 — Tariff exposure with pre-scored BOM | Planned | Week 10 |  |  | ~200 | Screenshot | Platform capability post.
19 | Video | What hides below Tier 2 — 2-min explainer | Planned | Week 10 |  |  | Script: 200 words | Iceberg visual | Script to write; film/produce.
20 | Video | The Substitution Trap — 2-min explainer | Planned | Week 11 |  |  | Script: 200 words | SmCo/NdFeB comparison slide | Use Slide 3 story as script basis.
21 | Document | Conversation Starter — for LinkedIn consultants | Planned | Week 12 |  |  | 2 pages | None | Leave-behind PDF.
22 | Document | Pilot Offer — 30 days, one plant, one vehicle line | Planned | Week 12 |  |  | 1 page | None | Not a pricing sheet.
23 | LinkedIn – Company | Pilot offer soft launch post | Planned | Week 12 |  |  | ~200 | None | CTA to contact page.
24 | LinkedIn – Company | Did You Know series (ongoing) | Planned | Ongoing |  |  | ~150 each | Stat cards | Batch 8–10 posts in advance.
25 | LinkedIn – Company | Product milestone posts | Planned | As needed |  |  | ~150 each | None | Factual announcements.
26 | LinkedIn – Founder | Live event analysis (tariff / disruption) | Planned | As needed |  |  | ~400 each | None | React with analytical depth.
27 | Partnership | ECC + Semantic Visions combined post | On Hold | Post-partnership |  |  | ~800 | None | SV partnership required. Draft now.
28 | Partnership | ECC + Total Materia combined post | On Hold | Post-partnership |  |  | ~800 | None | Total Materia formalised.
29 | Partnership | Neo4j Customer Advocacy brief | On Hold | Post-partnership |  |  | 1 page | None | Written for a Neo4j customer.
30 | Blog | Cross-Cutting Context Objects: Threading Structured Evidence Through a Multi-Engine Pipeline | Ready | Week 2–3 |  | Blog2_CrossCuttingContext_REVISED.md | ~2,200 | Diagram1_ExplanationContext_Flow.html + Diagram2_ExplanationStep_Anatomy.html → PNG | Engineering Excellence Blog 2 (publishes FIRST in series). All files complete. Screenshot diagrams via Chrome DevTools for Wix.
31 | Document | Data-Driven White Paper — Material Genealogy Case | In Progress | Parallel workstream |  |  | 6–8 pages | None | DECISION: parallel workstream — begin when user signals readiness. Not deferred to Month 4.
32 | Document | Analyst Briefing Document (Gartner/Forrester/IDC) | Deferred | Month 5 |  |  | 2 pages | None | After first customer/pilot.
33 | Blog | Conference Abstract — What No Supplier Map Can See | Deferred | After first pilot |  |  | 500 words | None | AutoSens / Automotive Logistics SC.
34 | Blog | Deterministic Cores, Agentic Shells — An Architecture Pattern for AI-Augmented Computation | Planned | After Blog 2 |  |  | ~2,000 | 3 diagrams (Three-Layer Stack, Crash Safety Tree, FTA Bug Before/After) → PNG | Engineering Excellence Blog 1 (publishes 2nd). VS Code Copilot content required. Uber/Netflix style.
35 | Blog | Phase-Ordered Graph Computation — Batch Pre-Compute Across 170K Interconnected Nodes | Planned | Engineering series (3rd) |  |  | ~2,200 | 4 diagrams (Phase DAG, PENDING Checkpoint, Algorithm Before/After, Batch Timeline) → PNG | Engineering Excellence Blog 3 (publishes 3rd). VS Code Copilot content required. Uber/Netflix style.
36 | Blog | State Machines as Agent Guardrails — Constraining Autonomous Workflows Through Explicit Transitions | Planned | Engineering series (4th) |  |  | ~1,800 | 3 diagrams (6-State Machine, Guardrail Layers, Rejected State Skip) → PNG | Engineering Excellence Blog 4 (publishes 4th). IP NOTE: no internal guardrail numbering — use 'write fence'. VS Code Copilot content required.
37 | Blog | Additive Extensibility — Engineering a System That Grows by Configuration, Not Code Modification | Planned | Engineering series (5th) |  |  | ~1,800 | 4 diagrams (Weight Normalization, Phase Registry, Predicate UI, 3 Hardcodes Gap Map) → PNG | Engineering Excellence Blog 5 (publishes 5th). VS Code Copilot content required. Includes honest 3-hardcodes limitation.
38 | Blog | Orchestrating Reactive Resilience — Small Model, Scoped Decisions in a Supply Chain Copilot | Deferred | After founder LinkedIn on copilot architecture |  |  | ~1,200 | Architecture diagram (moderate level) | Nvidia NIM 8B. Used as-is, not fine-tuned. Architecture at moderate level OK — copilot code not open-sourced. MUST be preceded by founder LinkedIn post.

## Legend
Legend — Status & Channel Colour Codes
Status Codes
Ready | Content is written, reviewed, and ready to publish
Planned | Scheduled in the calendar — not yet started
In Progress | Currently being written or produced
On Hold | Blocked by a dependency (partnership, data, etc.)
Deferred | Deliberately pushed past Week 12
Done | Published / delivered
Channel Codes
Blog | Long-form article for ecocomitychain.ai/blog
LinkedIn – Company | Post from EcocomityChain.AI company page
LinkedIn – Founder | Post from founder's personal page (higher reach)
Video | 2-min short-form video — script + visuals
Document | PDF leave-behind, white paper, or briefing document
Slide Deck | Presentation slide (adds to marketing deck)
Partnership | Co-marketing content — requires partnership confirmation